## Project Estimates
TASK (FRAMEWORK LEVEL) | INTERFACE | DAYS EFFORT ESTIMATE | VENDOR INTERFACE | MANAGER INTERFACE | NOTES
Clarify hosting & technology prerequisites | VENDOR/MANAGER/USER | 0.5 | 0.5 | 0.5 | SQL Server Agent + Full Text Search
Create ORM | VENDOR/MANAGER/USER | 2.5 | 2.5 | 2.5
Create POCO objects | VENDOR/MANAGER/USER | 1 | 1 | 1
Develop master page | VENDOR/MANAGER/USER | 2 | 2 | 2
Implement ASP.Net membership model with custom roles | VENDOR/MANAGER/USER | 1 | 1 | 1
Develop website stylesheets | VENDOR/MANAGER/USER | 3 | 3 | 3
Implement Jquery/Kendo libraries | VENDOR/MANAGER/USER | 0.5 | 0.5 | 0.5
Create view model | VENDOR/MANAGER/USER | 2 | 2 | 2
Create data input objects | VENDOR/MANAGER/USER | 1.5 | 1.5 | 1.5
Perform unit tests | VENDOR/MANAGER/USER | 15 | 15 | 15
Create database objects | VENDOR/MANAGER/USER | 1 | 1 | 1
Configure IIS | VENDOR/MANAGER/USER | 1 | 1 | 1
TOTAL DAYS ESTIMATE FOR GROUP |  | 31 | 31 | 31
TASK (SECURITY SPECIFIC) | INTERFACE | DAYS EFFORT ESTIMATE | VENDOR INTERFACE | MANAGER INTERFACE | NOTES
Implement ReCaptcha code library via NuGet | VENDOR/MANAGER | 1 | 1 | 1
Develop login form | VENDOR/MANAGER | 1 | 0.5 | 0.5
TOTAL DAYS ESTIMATE FOR GROUP |  | 2 | 1.5 | 1.5
TASK (TASK LEVEL) | INTERFACE | DAYS EFFORT ESTIMATE | VENDOR INTERFACE | MANAGER INTERFACE | NOTES
Develop "Vendor cockpit" | VENDOR | 1 | 1
Develop RHS side panels | VENDOR/USER | 2 | 2 |  | Still in scope?
Develop Administration centre form | VENDOR | 1 | 1
Develop "Follow us" object | VENDOR | 1 | 1 |  | Investigate how to do this.
Develop "Add administrator" form | VENDOR | 0.5 | 0.5
Develop "Add editor" form | VENDOR | 0.5 | 0.5
Develop "Add finance contact" form | VENDOR | 0.5 | 0.5
Develop "Active/inactive categories" form | VENDOR | 4 | 4 |  | Will need to confirm new sub category implementation before accurate estimation.
Develop "Invoice centre" form | VENDOR | ??? | ??? |  | Still in scope?
Develop invoice object | VENDOR/MANAGER | ??? | ??? | ??? | Still in scope?
Develop "PAY NOW" form | VENDOR | ??? | ??? |  | Still in scope?
Develop payment method object | VENDOR | ??? | ??? |  | Still in scope?
Develop "Content centre" form | VENDOR/MANAGER | 3 | 1.5 | 1.5 | Will need to confirm new sub category implementation before accurate estimation.
Develop cloudware package list object | VENDOR | 0.5 | 0.5 |  | Still in scope?
Develop content categories object | VENDOR | 0.5 | 0.5 |  | Still in scope?
Develop "Marketing centre" form | VENDOR | 0.5 | 0.5 |  | Still in scope?
Develop "Change package" form | VENDOR | 0.5 | 0.5 |  | Still in scope?
Develop "Request sponsorship package" form | VENDOR | ??? | ??? |  | Still in scope?
Develop generic "Thank you..." form | VENDOR | ??? | ??? |  | Still in scope?
Develop "Support centre" form | VENDOR/MANAGER | 2 | 1 | 1 | Do we need a facility to add questions?
Develop "FAQs" object | VENDOR/MANAGER | 0.5 | 0.5 | 0.5 | Are questions categorized?
Develop "Ask question" form | VENDOR | 0.5 | 0.5 |  | See above re categorising questions.
Develop "Register cloudware for FREE" form | VENDOR | 1 | 1 |  | Use existing feature? If so, not really part of the VX solution. May be misunderstanding the workflow - does a vendor need to register as a vendor i.e. be given login details before they can register any cloudware? Or is it just the MX which allows a manual creation of the vendor on receipt of an email via the current register cloudware page?
Develop package summary purchase form | VENDOR | 1 | 1 |  | Page 41 "Select your cloudware package" - is this still in scope i.e. Pay online?
Develop package summary object | VENDOR | 0.5 | 0.5 |  | Page 42 & 43 of VX. See above.
Develop "What happens next" form | VENDOR | 0.5 | 0.5 |  | Still in scope?
Develop "Thanks for choosing the XXX package" form | VENDOR | 0.5 | 0.5 |  | Still in scope?
Develop "Step 1" form | VENDOR | 1 | 1 |  | Still in scope?
Develop "Step 2" form | VENDOR | 10 | 5 | 5 | Revamp of existing VX interface. This is the "Creation of vendor", "Creation of service for existing vendor", "Modify existing service". Need to clarify the logic for a video inclusive package.
Develop "Step 3" form | VENDOR | 0.5 | 0.5 |  | Still in scope?
Develop data driven text object / administration of metadata | MANAGER |  |  | ??? | Do we need an MX interface to manage the content of Company/Cloudware Explained etc.?
Develop "Administrator cockpit" form | MANAGER | 0.5 |  | 0.5
Develop "Content approval" object | MANAGER | 1 |  | 1
Develop "Support questions" object | MANAGER | 1 |  | 1
Develop "Our compare cloudware centre" form | MANAGER | 1 |  | 1
Develop "Manage users" object | MANAGER | 3 |  | 3
Develop "Manage content" object | MANAGER | 0.5 |  | 0.5
Develop "Vendor administrator settings" object | MANAGER | 0.5 |  | 0.5
Develop "Content approval" object | MANAGER | 0.5 |  | 0.5 | Will use the VX interface like for like.
Develop "Registered vendors" object | MANAGER | 0.5 |  | 0.5
Develop registered vendor detail object | MANAGER | 2.5 |  | 2.5
Develop invoices form | MANAGER | ??? |  | ??? | Still in scope?
Develop "Manage vendor" form | MANAGER | 1 |  | 1
Develop sub-categories menu | VENDOR/MANAGER/USER | ??? |  | ???
Develop extra logging of site analytics | USER | 2 |  |  | Record all autocomplete entries
Logging of logins | VENDOR/MANAGER | 1 | 0.5 | 0.5
Create category | MANAGER | ??? |  | ??? | Will need to confirm new sub category implementation before accurate estimation.
Create new service | MANAGER | 2 |  | 2
Exporting of Web API data to EXCEL. | MANAGER | 4 |  | 4 | Clarify input parameters e.g. Date ranges, category, vendor etc. Clarify sorting capabilities. Clarify field selection/inclusion for content. Clarify destination e.g. Local download, email etc.
Enhanced vendor usage reporting. | VENDOR/MANAGER | ??? | ??? | ??? | To discuss & clarify.
TOTAL DAYS ESTIMATE FOR GROUP |  | 54.5 | 26.5 | 26.5
BUG FIXING / TESTING / PUBLISHING / ADMIN factor |  | 40% | 40% | 40%
OVERALL PROJECT PLAN TOTAL ESTIMATE |  | 87.5 | 59 | 59
OVERALL PROJECT PLAN TOTAL ESTIMATE FACTORED |  | 122.5 | 82.6 | 82.6